Table of Contents

Event Agenda	2

Participant Expectations	2

Reference Materials	3

Updated Documentation for Sept 2025 with Strategic Directions and Implementation Timelines	3

Strategic Directions Team Reports	3

Environmental Scan Using S.W.O.T	5

Implications for our Planning	6

Dean’s Update	6

Curriculum Adaptation Discussion	7

Engaging Faculty	8

Year Two Implementation Timeline	9

Coordination	11

# Event Agenda

|  | Tues | Wed | Thurs |
| --- | --- | --- | --- |
| Morning | 9am Opening, Check-in |  | 9am Open |
|  | Refresh Strategic Plan Product In SD Teams - Annual Review / Reports |  | Cross-Walk Timeline to Updated Envision Templates |
|  | Crowd-source key questions to get input from the Leadership Team on |  | Cross-Tag CHHS SD to University Strategic Plan |
| Lunch | 11:30 - 1:00 Lunch |  | 12 - 1pm Lunch |
| Afternoon | SWOT Env Scan Dean’s Report - Changes to Financial Aid & Implications Discussion: Guidance on how to adapt our degree programs to new financial aid reality & IPE crosswalk simultaneously | Provocative Proposals: Timeline deliverables Strategic Directions Teams - Propose Updated Deliverables for 2026 Review and Prioritize | Celebration of the Team & the Year’s Accomplishments 2pm Close |
|  | Brainstorm: How to get faculty engaged in the adaptation process? | Build Implementation Timeline |  |

# Participant Expectations

- Make decisions, tweak and move forward but not start all over. Avoid overwhelm. Keep steady.

- Taking stock.

- Reflect on our accomplishments / morale.

- Resetting our strategic priorities

- Updates on what the President / Provost thinking

- IPE Director PD approval - refresh the IPE committee role

- Define the roles of the Point persons for the SD’s & how Envisio is being managed

- Planning for the next year

- Seeing what opportunities there are based on progress from the last year (training, acad, etc)

- Expectations for Envisio updating & ensuring it’s relevance

- WMU 4year plan - how to fit in.

# Reference Materials

August 2024 Strategic Planning Event Documentation

WMU CHHS Leadership Retreat Documentation v2.docx

Updated Documentation for Sept 2025 with Strategic Directions and Implementation Timelines

# Strategic Directions Team Reports

| Strategic Direction: [Re]Igniting College Pride and Belonging Team Members: |  |
| --- | --- |
| Accomplishments: - Belonging survey, college wide and communications survey - Collected info from depts-snapshot of communication - Events: Chili Cookoff, potluck, faculty/staff awards, 8 lunch and learns, movie nights - Marketing Plan - Capital, Homecoming tailgate and sponsoring 5K - CHHS shirts - Book Club - Major growth in social media engagement–need to expand to tiktok, student “challenges” | Challenges: - Committee availability–lack of participation in college - Empty building - Lost Betty and Trevor - Growth of online programs - Housing and food was a disaster this wummer–no “college pride” during 6 week summer programs |
| Recommendations for Year 2: - Coordinate day of service with RSOs and community partners - Re-establish lunch and learn for students/faculty/staff - Graduate Lounge - Graduate students should be working in person–no remote work–this helps with empty building - Bring students into committee to shape how to engage them - Rotate lunch and learn across departments? Determine overall purpose to determine ROI | Key Questions to Address Together: Who (students/student groups) can we add to our committee to complete our work–MRO? |

| Strategic Direction: Modernizing our Systems and Procedures Team Members: |  |
| --- | --- |
| Accomplishments: - EXXAT - Completed System Survey - HR Process Drafts - Employee Handbook Draft | Challenges: - University Systems - Timelines (short / long) - EXXAT - cost per student apprehension |
| Recommendations for Year 2: - Finalizing HR onboarding / training - Classroom scheduling - Handbook implementation - All systems go! | Key Questions to Address Together: Should we split into two teams (University / College Systems) University - Advocacy and Influence College - Current systems change efforts Address the challenge of timelines of systems change with just one group taking them on. Answer - group trusts the judgement of the team to decide this. |

| Strategic Direction: Collaborating Internally and Externally Team Members: |  |
| --- | --- |
| Accomplishments: - Curriculum mapped to IPEC - Identified IPE experts - IPE director: recommended job description - IPE CHHS committee & CIEW attended virtual IPEC conference - Outside employment form: added survey R/T community boards - IAI | Challenges: - Role configuration (who has the ball) - own the process - Schedules - how to collaborate with all the different course schedules |
| Recommendations for Year 2: - Hire IPE Director - Establish CHHS IPE committee roles / objectives - Website - Needs assessment - External partner database | Key Questions to Address Together: |

# Environmental Scan Using S.W.O.T.

| What do we need to understand about our current context to ensure we update year 2 appropriately? |  |
| --- | --- |
| STRENGTHS | OPPORTUNITIES |
| Planning - We have a plan 🙂 - We have a plan !! - Tracking data to start data informed decision making - Keeping students at the center of planning - UC/CDS is now involved in conversations Personelle - Leadership support for innovation - Faculty engagement (mixed) - Collegial chairs and directors - More hiring in critical areas (good hires!) - Better staffed (Qty and Qlty) Programming - Recession proof programming - Well established programs - Success of HSV 1000 - Healthy & Supportive Leadership all the way up | Leadership - New leadership aligned with professional programming - Dedicated college leader - New Development officer - Build a Brand - Oracle EHR Community - Becoming the Community Hub - Community Partnerships - Developing Community College Partnerships - Community Partnerships - Program agreements (free college) Space - Good time to: connect with Alumni - Good time to: Build a common core curriculum in Health Sciences (& Service Learning) - Good time to: Clarify roles & expectations |
| WEAKNESSES | THREATS |
| Faculty / Staff Cognitive Load Disincentivizing Innovation - Faculty / staff fatigue / disengagement - status quo /walk systems if we fail to follow through - % of staff are not onboard yet - Faculty hesitancy / mistrust / lack of engagement - Innovation / hesitation / risk aversion / cognitive load Plan Refinements - Lack of Strategic Enrollment Plan - Do not have well-defined metrics - Don’t have a purposeful engagement plan (though we agree to keep moving with or without full engagement) Facilities that don’t meet our needs / facilities group Fragmented & small degree programs HR understanding of Needs | Enrollment / Competition - Growing conversation about need for higher education - Working in areas under threat - disability - H. Ed., DEI, etc - Demographic Clllliiiiffffff - Increased competition - Community college is now free - Not responding proactively & timely to needed change - enrollment Funding - Grant programs - Big Beautiful Bill & Decreased funding - Funding environment (federal, State, Student - Cost of education increasing Infrastructure - Infrastructure - Tech costs and time needed to master them effectively Endurance / Resilience / Fatigue - Overworking - increased expectations but less time - Lose momentum |

# Implications for our Planning

- We are putting together a good foundation

- Infrastructure to release innovation is needed

- Plan refinements needed: Metrics, Strategic Enrollment, Faculty & Staff Engagement

- “Rightsize” and then grow in the areas that the data points - “strategic enrollment management"

- Efficiency needs to be a focus going forward

- Diversifying our funding portfolio

- Reorganize our space in CHHS - deal with infrastructure issues

- Hire a Development officer (securing the Alumni Data)

- Deepen relationships with community

- Research & discovery for EHIR

- Building a common core curriculum

- Deans advisory board / program advisory boards - is there overlap can they occasionally meet together?

- Unified Clinics - A clear statement on behalf of CHHS as to how it benefits our purpose and our cost share.

# Dean’s Update

| Strategic Direction: Dean’s Office Team Members: Lillian, Jasmine, Alex, Joshua, Christopher |  |
| --- | --- |
| Accomplishments: - Envisio & analytics dashboard - SEC reorganized + project manager - Pathway U in place - Community Event help and did another - Hired Christopher and have a plan More: Started on workload DAB, New partnerships THRIVES, Wrote grant UC Business and personnel plans Research Foundation ADAA and other DO hires | Challenges: - HR, not being fully staffed - Leave policy (use it or lose it) - Uncertainty with UC, EWB, partnerships, UC - Lack of data - Resistance to change - Lack of focused strategies to bring faculty/staff on board |
| Recommendations for Year 2: - Building - Community Hub - Finalize workload and implementation plan - Refine Envisio and tie to WMU plan - Clarify and document procedures–research, committees, etc | Key Questions to Address Together: - Faculty and staff involvement - Integrating IPE and curriculum - Adjustment to new financial aid model - Implement workload distribution - Determining metrics and baselines |

| - Determine appropriate budgets for units and develop methods and metrics for financial distribution - Refine/define CHHS metrics for CHHS Strategic plan - Plan for financial aid | - Integrating THRIVES across strategic directions - Building |
| --- | --- |

# Curriculum Adaptation Discussion

What are the Pros and Cons of adapting / elongating degree programs to stay +/-

$40,000?

Directions and Guidance for How We Might Adapt our Degree Programs

- Focus on seeking innovative change vs adapting simply to stay under the federal student loan cap

- Take core and get it funded by Kalamazoo Promise

- Where viable, elongate, push coursework ‘to the coasts’ to stay with the federal student loan cap. Consider staying within summers.

- Highest value: How can we best train our students

- Keep flexibility for grants

- Adapt for pedagogical reasons

- Caution about losing students if we elongate beyond what’s an appealing timeline to graduation.

- If not a change in curriculum, if we are just rescheduling current credit hours, it does not have to go through the burdensome University approval process.

# Engaging Faculty

What are innovative yet effective ways to engage our faculty in the adaptation of degree programs?

| Communications with Faculty | Leadership Resourcing | Prototype and Try | Faculty Champions |
| --- | --- | --- | --- |
| Host interdepartmental forums Series of Listening Sessions / Faculty Meetings | Leadership team will support and provide resources for implementation College-Wide Innovation Committee with members from each Departmental Curriculum Comm. (Could be current college-wide Curric Comm) Incentivize: - Faculty release time (workload), Reward collaboration through co-teaching opportunities etc. Training Program for IPE | Come with proposed plan (and be flexible to change) | Faculty fellowship / champion |
| Meet (Associate or Dean) with faculty to introduce idea |  | Identify working model (practical) | Gain initial support from Key People |
| Planned interactions in Department meetings |  | Identify pilot - underenrolled, core courses, good research |  |
| Listening sessions - group faculty by expertise - staff recording or leading the sessions Ask faculty opinions transparently |  | PT / OT summer research course - 2 credits - could be part of the model |  |
| Communicate (narrative) need for change r/t student burden |  |  |  |
| Start the conversation form the student-centered focus |  |  |  |
| Opportunity for 1:1 meetings with Chair / Director |  |  |  |
| Anonymous survey - Open feedback channels for assessment |  |  |  |
| Find common ground / interests among faculty in adapting |  |  |  |
| Later…. Listening session focus groups with students |  |  |  |

# Year Two Implementation Timeline

Participants were asked to regather as Strategic Directions Teams and review the proposed deliverables that emerged from the thematic working groups, and add deliverables that build off the recommendations they made in their initial reflections on year one. They were then asked to ascribe a lead and a deadline to build the timeline below. Leads are bolded next to the task. The role of the lead is simply to ‘own’ the task in Envisio, do or delegate the work, track progress and be prepared to report back at check-in meetings.

| Implementation Activities for Year Two , to be reviewed and updated Quarterly |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Strategic Direction | Team Members | Q2 Oct - Dec ‘25 | Q3 Jan - Mar ‘26 | Q4 April - June ‘26 | Q1 Jul - Sep ‘26 | Year Three |
| (Re) Igniting College Pride, | *Ann* Jill Kyoung Melinda Neale Scot | Submit lunch and learn proposal to Dean Melinda & Jill Plan / Action items for Strategic Enrollment Scot (Form Strategic Enrollment Committee, Muti-faceted document including needs of dept, no one size fits all, review of existing data, reliable workforce data) Integrate Workforce Needs Assessment Into Strategic Enrollment Plan Neale, Ann Dec | Start Lunch and Learn Melinda & Jill Messaging framework that appeals to self-interest - Video Jill Monthly out & about check-ins with people in and out of CHHS building by Directors and Chairs | Messaging framework that appeals to self-interest - Video Jill Monthly out & about check-ins with people in and out of CHHS building by Directors and Chairs | Messaging framework that appeals to self-interest - Video Jill Monthly out & about check-ins with people in and out of CHHS building by Directors and Chairs |  |
| Engagement and Belonging |  | Messaging framework for faculty - Video clip from Lillian embedded in the Newsletter - Rules / Appeal to self-interest Jill |  |  |  |  |
|  |  | Create a google sheet for communication feedback from staff / faculty Crystal Dec |  |  |  |  |
|  |  | Monthly out & about check-ins with people in and out of CHHS building by Directors and Chairs |  |  |  |  |
| Modernizing our | *Drew* Mariann | Form Space Committee of stakeholders - start monthly | Host open forums (1? 2?) with FOOD for feedback Robin, Amy, | Influence University Systems (Monthly Meetings ) All | Build measures in Envisio Platform (Community Behavioral Health Data) | Produce a recommenda tion for space |

| Infrastruc-ture | Amy Crystal Robin Joshua | meetings Robin & Amy Finalize HR Training & Onboarding Mariann Schedule Richard C. for training (classroom schedule) Drew | Drew Finalize Employee Handbook Drew, Mariann |  | Joshua, Crystal July | Drew with All |
| --- | --- | --- | --- | --- | --- | --- |
|  | *Lisa* Nancy Dawn | Compiled survey data into a database Scot Oct Listening Sessions (2) with faculty IPE Committee / Associate Dean Oct | Funding model for IPE created Dean / Associate Dean / Research Jan | Update IPE Website IPE Director April | Pilot - OT 6008/PT62080 Summer 2 2026 - Research Methods - 54 students - Room 1093 Nancy, Amy, Robin Summer 2, 2026 | Hold innovation committee |
| IPE Curriculum Collaboration |  | Dean / Associate Dean present (15 min) information about the need for Curriculum Adaptation to departments in Dept meetings Dean / Assoc Dean Oct IPE College Committee uses IPEC resources (assessment / training) IPE Director Dec | Completed needs assessment for curriculum internally Scot Jan Faculty workload credit for IPE innovative design - mechanism app / review IPE Director March |  | Data analysis - solution options Scot & IPE Director Sept Student survey with Pilot Su-II Research Course Based on SWOT Associate Dean for Research Aug |  |
|  |  | Decide on options (re: Curriculum Adaptations) Dean December |  |  |  |  |
| Community Collaboration | *Chris* Kieran Lillian Neale | IPE Director Hired Dean / Assoc Dean Oct Associate Dean Listening session with each individual Department (re: workload, space, study abroad, etc). Neale Dec Workforce needs assessment plan Neale & Ann Dec CAST Tool assessment coordination | Funding model for IPE created Dean / Associate Dean / Research Jan Completed needs assessment externally (linked to workforce needs assessment - including community opportunities / needs and services) Scot Jan | Update IPE Website IPE Director April |  |  |

| Dean's Office | Lillian Jasmine Alex Neale Chris Crystal | Confirm a University that implemented an EHR that we need / works Crystal, Christopher Nov Determine the EHR that will meet UC needs Christopher, Crystal Dec Feasibility assessment on AI Chrisopher Dec Refine Envisio and tie to WMU plan Joshua, Enos Dec Refine / define CHHS metrics for CHHS strategic plan Neale Dec | Create funding model for UC / students Christopher Feb | Create a guide on CAST for Behavioral Health Rob June | Finalize workload and implement plan Alex Summer Determine appropriate budgets for units and develop methods and metrics for financial distribution Lillian Summer |  |
| --- | --- | --- | --- | --- | --- | --- |

# Coordination

- Tasks will all be entered into Envisio each Quarter

- Once a quarter, the plan will be the subject of the College Council meeting and teams will check in on progress.

- Strategic Directions Teams will continue to meet monthly.

- The Community Collaboration Strategic Direction (broken off from what was formerly “Collaborating Internally and Externally”) will meet alongside the Dean’s Office (given that there is a lot of crossover in people) and continue to pursue both workstreams for now. That decision can be revisited at a future quarterly CheckIn

- The Role of Team Leads:

  - New Team Leads were identified for each Team (see bolded names). Expectations for their role include

  - Coordinating the monthly meetings

  - Updating Envisio (unless they’ve specifically delegated it to another team member who owns the task)

  - Updating Envisio at the Strategic Direction Level

  - Pulling Reports for the Strategic Direction for Quarterly check-in meetings

  - Adding (or ensuring it is being done by someone) new actions and ensuring they are tagged and / or cloned to the Strategic Plan.

……